{"text_format":"3","workbook":"xls","n_sheets":1,"sheets":["EFT Change Requests"],"not_rendered":{"external_links":2,"defined_names":1},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"EFT Change Requests","index":0,"n_rows":50,"n_cols":15,"rows_kept":50,"merged":[[1,1,1,10],[9,2,11,2],[9,3,11,3],[9,4,11,4],[9,5,11,5],[9,6,11,6],[9,7,11,7],[9,8,11,8],[9,9,11,9],[9,10,11,10],[9,14,11,14],[12,2,14,2],[12,3,14,3],[12,4,14,4],[12,5,14,5],[12,6,14,6],[12,7,14,7],[12,8,14,8],[12,9,14,9],[12,10,14,10],[12,14,14,14],[15,2,17,2],[15,3,17,3],[15,4,17,4],[15,5,17,5],[15,6,17,6],[15,7,17,7],[15,8,17,8],[15,9,17,9],[15,10,17,10],[15,14,17,14],[18,2,20,2],[18,3,20,3],[18,4,20,4],[18,5,20,5],[18,6,20,6],[18,7,20,7],[18,8,20,8],[18,9,20,9],[18,10,20,10],[18,14,20,14],[21,2,23,2],[21,3,23,3],[21,4,23,4],[21,5,23,5],[21,6,23,6],[21,7,23,7],[21,8,23,8],[21,9,23,9],[21,10,23,10],[21,14,23,14],[24,2,26,2],[24,3,26,3],[24,4,26,4],[24,5,26,5],[24,6,26,6],[24,7,26,7],[24,8,26,8],[24,9,26,9],[24,10,26,10],[24,14,26,14],[27,2,29,2],[27,3,29,3],[27,4,29,4],[27,5,29,5],[27,6,29,6],[27,7,29,7],[27,8,29,8],[27,9,29,9],[27,10,29,10],[27,14,29,14],[30,2,32,2],[30,3,32,3],[30,4,32,4],[30,5,32,5],[30,6,32,6],[30,7,32,7],[30,8,32,8],[30,9,32,9],[30,10,32,10],[30,14,32,14],[33,2,35,2],[33,3,35,3],[33,4,35,4],[33,5,35,5],[33,6,35,6],[33,7,35,7],[33,8,35,8],[33,9,35,9],[33,10,35,10],[33,14,35,14],[36,2,38,2],[36,3,38,3],[36,4,38,4],[36,5,38,5],[36,6,38,6],[36,7,38,7],[36,8,38,8],[36,9,38,9],[36,10,38,10],[36,14,38,14],[39,2,41,2],[39,3,41,3],[39,4,41,4],[39,5,41,5],[39,6,41,6],[39,7,41,7],[39,8,41,8],[39,9,41,9],[39,10,41,10],[39,14,41,14],[44,2,44,10],[45,2,45,10],[46,2,46,10],[47,2,47,10],[48,2,48,10],[49,2,49,10]],"flags":["formulas_cached_only"]}
[]
[null,"EFT Change Request\nSummary Sheet"]
[]
[null,"Meeting Reference",null,"E.ON Földgáz Trade"]
[null,"Last Update",null,"2009-12-14"]
[null,"Attendees",null,"n/a"]
[null,"Meeting Number",null,"n/a"]
[]
[null,"REF\n#","DATE\nRAISED","CHANGE DETAILS","CR-OWNER","EFT APPROVED?","COST","DUE\nDATE","UPDATE\nCOMMENTS","STATUS","COMPLETION\nDATE","EFFORT BREAKDOWN","EFFORT","COST\nBreakdown","Total Cost"]
[null,"EFT CR-001","2009-07-03","Network Point Groups\nEntry-Mandatory Offer Contract Types","Péter Hatala","YES",{"v":32025,"d":"£32,025.00"},"2009-10-30","05/11/09 - EFT have confirmed UAT as complete.\n","DELIVERED","2009-11-05","Analysis, Design & Unit Spec \n","n/a",null,{"v":32025,"d":"£32,025.00"}]
[{"$nulls":11},"Development","n/a"]
[{"$nulls":11},"Testing","n/a"]
[null,"EFT CR-002","2009-11-02","Screen Usability Changes","Péter Hatala","YES",{"v":4812.5,"d":"£4,812.50"},"2009-12-14","02/11/09 - Change Raised","DELIVERED",null,"Analysis, Design & Unit Spec \n",0.6,{"v":525,"d":"£525.00"},{"v":4812.5,"d":"£4,812.50"}]
[null,"EFTCS2009.03",{"$nulls":9},"Development",4.2,{"v":3675,"d":"£3,675.00"}]
[{"$nulls":11},"Testing",0.7,{"v":612.5,"d":"£612.50"}]
[null,"EFT CR-003","2009-11-02","Online User Registration","Péter Hatala","YES",{"v":14000,"d":"£14,000.00"},"2009-12-14","02/11/09 - Change Raised","IN PROGRESS",null,"Analysis, Design & Unit Spec \n",1.75,{"v":1531.25,"d":"£1,531.25"},{"v":14000,"d":"£14,000.00"}]
[null,"EFTCS2009.04",{"$nulls":9},"Development",10,{"v":8750,"d":"£8,750.00"}]
[{"$nulls":11},"Testing",4.25,{"v":3718.75,"d":"£3,718.75"}]
[null,"EFT CR-004","2009-11-02","Modification to nomination template validation","Péter Hatala","YES",{"v":3500,"d":"£3,500.00"},"2009-12-14","02/11/09 - Change Raised","DELIVERED",null,"Analysis, Design & Unit Spec \n",0.4,{"v":350,"d":"£350.00"},{"v":3500,"d":"£3,500.00"}]
[null,"EFTCS2009.05",{"$nulls":9},"Development",3.2,{"v":2800,"d":"£2,800.00"}]
[{"$nulls":11},"Testing",0.4,{"v":350,"d":"£350.00"}]
[null,"EFT CR-005","2009-11-02","Modification to multi-day nominations","Péter Hatala","YES",{"v":6125,"d":"£6,125.00"},"2009-12-31","02/11/09 - Change Raised","DELIVERED",null,"Analysis, Design & Unit Spec \n",0.6,{"v":525,"d":"£525.00"},{"v":6125,"d":"£6,125.00"}]
[null,"EFTCS2009.06",{"$nulls":9},"Development",5.1,{"v":4462.5,"d":"£4,462.50"}]
[{"$nulls":11},"Testing",1.3,{"v":1137.5,"d":"£1,137.50"}]
[null,"EFT CR-006","2009-11-02","SMS Messaging","Péter Hatala","YES",{"v":5250,"d":"£5,250.00"},"2009-12-31","02/11/09 - Change Raised","DELIVERED",null,"Analysis, Design & Unit Spec \n",0.6,{"v":525,"d":"£525.00"},{"v":5250,"d":"£5,250.00"}]
[null,"EFTCS2009.07",{"$nulls":9},"Development",4.8,{"v":4200,"d":"£4,200.00"}]
[{"$nulls":11},"Testing",0.6,{"v":525,"d":"£525.00"}]
[null,"EFT CR-007","2009-11-02","Nomination Energy Calculations","Péter Hatala","YES",{"v":4375,"d":"£4,375.00"},"2009-12-14","02/11/09 - Change Raised","DELIVERED",null,"Analysis, Design & Unit Spec \n",0.4,{"v":350,"d":"£350.00"},{"v":4375,"d":"£4,375.00"}]
[null,"EFTCS2009.08",{"$nulls":9},"Development",4.4,{"v":3850.0000000000005,"d":"£3,850.00"}]
[{"$nulls":11},"Testing",0.2,{"v":175,"d":"£175.00"}]
[null,"EFT CR-008","2009-11-02","Modification to the view nomination screen","Péter Hatala","YES",{"v":437,"d":"£437.00"},"2009-12-14","02/11/09 - Change Raised","DELIVERED",null,"Analysis, Design & Unit Spec \n",0,0,{"v":437.5,"d":"£437.50"}]
[null,"EFTCS2009.09",{"$nulls":9},"Development",0.4,{"v":350,"d":"£350.00"}]
[{"$nulls":11},"Testing",0.1,{"v":87.5,"d":"£87.50"}]
[null,"EFT CR-009","2009-11-02","Numeric Formatting","Péter Hatala","YES",{"v":9625,"d":"£9,625.00"},"2009-12-31","02/11/09 - Change Raised","IN PROGRESS",null,"Analysis, Design & Unit Spec \n",0.8,{"v":700,"d":"£700.00"},{"v":9625,"d":"£9,625.00"}]
[null,"EFTCS2009.10",{"$nulls":9},"Development",7.6,{"v":6650,"d":"£6,650.00"}]
[{"$nulls":11},"Testing",2.6,{"v":2275,"d":"£2,275.00"}]
[null,"EFT CR-010","2009-11-02","Modify message subscriptions for a user","Péter Hatala","YES",{"v":437.5,"d":"£437.50"},"2009-12-14","02/11/09 - Change Raised","DELIVERED",null,"Analysis, Design & Unit Spec \n",0,0,{"v":437.5,"d":"£437.50"}]
[null,"EFTCS2009.11",{"$nulls":9},"Development",0.4,{"v":350,"d":"£350.00"}]
[{"$nulls":11},"Testing",0.1,{"v":87.5,"d":"£87.50"}]
[null,"EFT CR-011","2009-11-23","Provision of a B2B interface with external systems","Péter Hatala","NO",{"v":13125,"d":"£13,125.00"},"TBC","23/11/2009 - Change Raised","RAISED",null,"Analysis, Design & Unit Spec \n",2,{"v":1750,"d":"£1,750.00"},{"v":13125,"d":"£13,125.00"}]
[null,"EFTCS2009.02",{"$nulls":9},"Development",10.9,{"v":9537.5,"d":"£9,537.50"}]
[{"$nulls":11},"Testing",2.1,{"v":1837.5,"d":"£1,837.50"}]
[{"$nulls":13},"2009-12-14",27562.5]
[null,"Key Discussion Points",{"$nulls":11},"2009-12-31",21000]
[null,"Dis 1",{"$nulls":12},48562.5]
[null,"Dis 2"]
[null,"Dis 3"]
[]
[null,"P1","All expenses are to be billed separately post delivery."]
[null,"P2","Payment is due upon delivery unless agreed otherwise."]